12/19
1/20
2/20
3/20
4/20
5/20
6/20
7/20
8/20
29
2
9
16
23
30
6
13
20
27
3
10
17
24
2
9
16
23
30
6
13
20
27
4
11
18
25
1
8
15
22
29
6
13
20
27
3
10
17
24
31
MRes project
  Scoping
      Pre-reading
      Workshops with marine experts
      Project design
      Finalise project scope
  Researching
      Researching
      End of research
  Writing
      Draft introduction
      Draft methology
      Writing - full time
      Draft dissertation to supervisor
      Feedback & polishing
      Hand in dissertation
  Relevant taught modules
      C-week
      Generalised linear modelling
      Ecological modelling
      Evolutionary modelling
      CMEE mini-project final push
Powered by TCPDF (www.tcpdf.org)